## Daily Schedule
WEEK AT A GLANCE |  | NOTES / TO DO LIST |  | Owner
| XML parser and change Request.txt to XML file |  | XML parser and change Request.txt to XML file | Marina
2020-06-02 | Documentation: (Flashing protocol description) | √
|  |  | After uploading file: (Report load successfully - Wait for 1 min for a flashing report from Rπ) | Nader
Tuesday |  | √
| Marker erased @ flash new app and written @ end flashing |  | Button check last file status (Activated after Timeout) | Nobe
2020-06-03 | Documentation: (Doxygen reports) | √
BaudRate: 115200
| Flash write sector (erase then write) |  | Documentation: (different types of servers and why google cloud) | 2andeel
Wednesday |  | √
| After uploading file: (Report load successfully - Wait for 1 min for a flashing report from Rπ) |  | Documentation: (JSON key and how to use) | Nader
2020-06-04 | Button check last file status (Activated after Timeout) | √
Python GUI error handling (check .elf file & not empty - upload file exceptions)
| PI: (Return status xml) |  | Python GUI error handling (check .elf file & not empty - upload file exceptions) | 2andeel
Thursday | PI: (GUI Interaction) | √
| Flash new app while app exists handling (2 Markers) |  | PI: (Return status xml) | Martha
2020-06-05 | Documentation: (different types of servers and why google cloud) | √
Documentation: (JSON key and how to use)
Friday | Search: UDS / unified diagnostic services |  | PI: (GUI Interaction) | Martha
| PI Screen | √
2020-06-06 |  |  | PI Screen | Martha
√
Saturday
|  |  | BaudRate: 115200 | Honda
√
2020-06-07
|  |  | Documentation: (Doxygen reports) | Nobe
Sunday |  | √
|  |  | Documentation: (Flashing protocol description) | Honda+2andeel
√
|  |  | Flash write sector (erase then write) | Nader
√
|  |  | Marker erased @ flash new app and written @ end flashing | 2andeel
√
|  |  | Flash new app while app exists handling (2 Markers) | Nobe
√
|  |  | Search: UDS / unified diagnostic services | Honda
√